## Ground Checklist
Commissioning Checklist (Rev 002)
Performed By: | Include notes here: | Date:
Customer Sign off
Customer Name(s): | Date:

## Spotter Installation
Spotter Installation
Task | Description | Completed (initials) | Verified (initials) | Notes
Install Radars and Cameras on poles and take pictures of each install (one looking at the radar or camera and another from behind looking out). Place pictures in Project Folder. | If installed by integrator or customer, verify that this has been done correctly by checking pitch, azimuth, install height and location. Radar Installation Quickstart Mount-1 Quickstart GX1500 Quickstart
Install power rails and test each radar cable with the SpotterRF Cable testing kit. | Radar Installation Quickstart Verify that this step has been done.
Connect each radar and camera to the power rail | Radar Installation Quickstart Verify that this step has been done and verify connectivity.
Take pictures of each enclosure showing specifically which devices are plugged into which port of the switch and place in project folder:
Install NetworkedIO servers, connect to security network and wire up contacts (if necessary) | NIO-DINs Quickstart NIO-DINm Quickstart Verify that this step has been done and verify connectivity.
Take Pictures of the NIO server and how it is networked/integrated to the VMS, Access Control and/or Alarm management system (if contacts are used show which contact triggers which action):
Set IP address for radars | Radar Installation Quickstart
Set IP address for cameras | This step will vary depending on camera manufacturer but generally: access the camera with the default IP address, go to networking tab, set IP address to the same subnet as your Spotter devices
Set IP address for NIO | NIO-DINm Quickstart NIO-DINs Quickstart NIO-VM Quickstart NIO-APP Quickstart

## Basic NIO Setup
Basic NIO Setup
Task | Description | Completed (initials) | Verified (initials) | Notes
Download Existing Configuration | Video Instruction: Put configuration file in Project Drive under sites,
NIO SETTINGS -set Name for NIO Server on settings page (SITE NAME)
Download Maps for site | Video Instruction: download maps for an area, upload map pack/region tiles or upload map from image
Get IP addresses, username and passwords, make sure all devices are functioning and upgraded | Request this information from customer.
Ensure radars and cameras have correct IP assignments | Compare to site plan. Discuss differences with PM, Have IP addresses and passwords in hand
Add all radars to NetworkedIO | Video Instruction:
Name all Devices in device list after customer specification | Video Instruction:
Move each radar to correct location on the map and approximate azimuth angle for each radar | Video Instruction: Use landmarks visible on NIO
Verify each radar has only one subscription | Video Instruction: Radar IP > Outputs > Active subscriptions; Ensure that the sp_host IP address matches the IP of the radar as seen in the browser IP address bar; delete all others
Add all PTZ cameras to NetworkedIO | Video Instruction: Use height above ground in meters for elevation
Move each PTZ camera to the correct geolocation | Video Instruction - Use landmarks visible on NIO
Set the NTP Server on NIO | Video Instruction
Ensure radar's NTP points to the NIO, NIO points to their NTP server | Video Instruction: Use the IP address of the NIO on the Spotters,
Adjust Track History Settings > Maximum Tracks | Video Instruction: Set to 250,000
Set port forwarding URLs if needed for each device and for NIO | Video Instruction: Get URL from customer
(Save to end) Add admin credentials to NIO | Video Instruction: Record credentials here: Username: Password:

## NIO Device Setup
NIO Device Setup
Task | Description | Completed (initials) | Verified (initials) | Notes
Verify status handlers for each radar | Video Instruction:
Verify status handlers for each camera | Video Instruction:
Add status handlers for each camera | See video instruction above
Test Status Handlers and make sure they are triggering the appropriate responses (when possible) | Video Instruction:
Set Health page thresholds on radar (you will likely need to adjust these as the system is tuned further, or as you see the behavior during the rest of the install) | Video Instruction:
Add admin account to radar (if required) keep in mind that if credentials are set on radar, it is more difficult to reset those than with NIO | Video Instruction: Record radar credentials here: Username: Password:
Add viewer account (if admin accounts are created) | See video instruction above There is generally no need to create a user account as users of the system will generally not be accessing the radar directly